## Sheet1
Array Summary Tool User Feedback https://github.com/aoifebar/Array-Summary-GUI
Owner | Product Code | Issued Identified | Status | Resolution Date | Resolution Git Commit
G, Prashanth | 8PNRCVB | Can we add the total number of dies/wafer pulled here for B98/99 data in the email? | Open
Barnes, Aoife |  | Vmin plots (for optimsation) - WIP just need to get JMPbackgroundcaller working. | Open
Barnes, Aoife |  | Vmin repeatability plots | Open
Bilei, Rocky | RPL8161 |  | N/A
Horan, Ciara | 8PRJCVA |  | N/A
Marsh Brendan | ADL081 |  | N/A
Cathcart, Thomas | 8PQGCVBJ | Can we update the target module field to take a list of modules, saves repeated running? | Closed | 23WW05.1 | 3102280
Cathcart, Thomas | 8PQGCVBJ | Print results to text file output as well as email? | Closed | 23WW05.1 | 3102280
Cathcart, Thomas | 8PQGCVBJ | Need to print out module name in emailed table. | Closed | 23WW05.1 | 3102280
G, Prashanth | 8PNRCVB | Operation is not being replaced by script in production TT tool | Closed | 23WW03.5 | 9bfd234